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	Item Description
	Completion[endnoteRef:1] [1: End Notes 2027 RMQ Annual Plan:
 Dates in the completion column are by end of the quarter for completion by the assigned committee and subcommittee.  The dates do not necessarily mean that the standards are fully staffed to be implementable by the industry, and/or ratified by membership.  If one item is completed earlier than planned, another item can begin earlier and possibly complete earlier than planned.  There are no begin dates on the plan.] 

	Assignment[endnoteRef:2] [2:  The assignments are abbreviated.  The abbreviations and committee structure can be found at the end of the Annual Plan document.] 


	1.
	Cybersecurity and Electronic Delivery Mechanism

	
	
	Review RMQ Cybersecurity Model Business Practices and Quadrant-Specific Electronic Delivery Mechanism Model Business Practices, including data fields and minimum technical characteristics, and revise as needed. 
Status:  Not Started
	3rd Q, 2027
	RMQ IR/TEIS 

	2.
	Distributed Energy Resources

	
	a)
	Consider and develop of business practices to support the creation of a universal DER entity Registry
Status: Started
	2027
	RMQ BPS

	
	b)
	Consider and develop of business practices to support the integration of DER management systems by the industry
Status: Not Started
	2027
	Joint RMQ BPS and WEQ BPS

	
	c)
	Develop additional business practices, as needed, to address any retail market specific considerations to support the integration of DER management systems
Status: Not Started
	2027
	RMQ BPS

	3.
	Energy Services Providers Interface 

	
	
	Consider and develop modifications to simplify ESPI Customer schema to match ESPI Energy schema IdentifiedObject assignment pattern – Request R26003
Status: Not Started
	2nd Q, 2027
	RMQ ESPI Task Force

	Program of Standards Maintenance & Fully Staffed Standards Work[endnoteRef:3] [3:  This work is considered routine maintenance and thus the items are not separately numbered. The RMQ EC will assign maintenance efforts on a request-by-request basis.] 


	
	a.
	Business Practice Requests
	Ongoing
	Assigned by the EC

	
	b.
	Information Requirements and Technical Mapping of Business Practices
	Ongoing
	Assigned by the EC

	
	c.
	Interpretations for Clarifying Language Ambiguities 
	Ongoing
	Assigned by the EC

	
	d.
	Maintenance of Code Values and Other Technical Matters
	Ongoing
	Assigned by the EC

	
	e.
	Development and Maintenance of Definitions
	Ongoing
	Assigned by the EC

	
	f.
	Harmonization of Definitions with All Other Quadrants
	Ongoing
	Assigned by the EC

	
	g.
	Development and Maintenance of Model Business Practices
	Ongoing
	Assigned by the EC

	Provisional Activities

	
	1.
	Upon a request or as directed by NAESB Board or a relevant jurisdictional entity, consider developing and/or modifying business practice standards that reflect best practices that will provide stronger operating reliability from production/supply/transport, for example, during extreme weather conditions, and more clear communications and business processes around force majeure declarations during critical operating periods.

	Retail Electric Model Business Practices Only	

	
	1.
	Develop and/or modify the NAESB Model Business Practices to address any requests regarding community solar or aggregated net metering.


RETAIL MARKETS QUADRANT EXECUTIVE COMMITTEE AND SUBCOMMITTEE STRUCTURE
Retail Markets 
Quadrant Executive Committee
(RMQ EC)
Business Practices Subcommittee (BPS)
Contracts Subcommittee (dormant)
Glossary Subcommittee
Retail Registration Agent Task Force (*)
Technical Electronic Implementation Subcommittee (TEIS)

Model Business
Practice
Development
Task Forces & Working Groups

Technical 
Standards
Development
Joint RMQ/WEQ Demand Side Management and Energy Efficiency (DSM-EE) Subcommittee
Information Requirements (IR) Subcommittee
Open Field Message Bus (FMB) Task Force
Energy Services Provider Interface (ESPI) Task Force


[bookmark: _Hlk115433854]NAESB 2027 RMQ EC and Subcommittee Leadership:
Executive Committee:  Debbie McKeever, Chair
Business Practices Subcommittee:  Debbie McKeever
Information Requirements Subcommittee/Technical Electronic Implementation Subcommittee:  Debbie McKeever
Glossary Subcommittee:  Debbie McKeever
DSM-EE Subcommittee:  Debbie McKeever
Retail Registration Agent Task Force:  Debbie McKeever
Open FMB Task Force:   Vacant 
Energy Services Provider Interface (ESPI) Task Force: Donald Coffin
(*) The Retail Registration Agent Task Force may draft MBPs, process flows, implementation guides and technical standards supportive of the Registration Agent and submit them to the BPS.  The group is chaired by Debbie McKeever.
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