## API Support Materials
NAESB WEQ-OASIS Subcommittee
2017 Annual Plan OPEN Items
2017 API # | Submitted Date | 1st Annual Plan Year | Description | Request/FERC Order | Docs | Assigned | Status | Remaining Steps | Target Completion Date | Assignment
2ai1 | 2005-06-24 | 2008 | Short-Term Firm Preemption and Competition (OATT Section 13.2 and 14.2) | R05019 | 2016 WEQ Annual Plan Items 2.a.i.1 and 5.a | OS | WEQ-001 out for informal comments. Comments due 11/11/2016 | WEQ-002,003,013 | 2nd Q 2017
5a | 2009-02-09 | 2010 | Add language to WEQ-001-4 Online Negotiation and Confirmation process to clarify Table 4-3 | R09003 |  | OS | WEQ-001 out for informal comments. Comments due 11/11/2016 | WEQ-002,003,013 | 2nd Q 2017
2aii1 | 2007-10-11 | 2008 | Paragraph 1627 of Order 890 – Posting of additional information on OASIS regarding firm transmission curtailments | 890 | weq_bps_oasis 090915w1 | OS/BPS | Initial positionpaper received from BPS. BPA accepted an individual assignment to capture associated parameters and challenges. No formal action taken to date. | OS to prioritize | TBD
weq_oasis062116a1 (BPA response)
2aii2 | 2007-10-11 | 2008 (2014?) | Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services. | 890 | weq-0asis 022416a2 BPS Feb 2016 | OS/BPS | Initial positionpaper received from BPS. BPA accepted an individual assignment to capture associated parameters and challenges. No formal action taken to date. | OS to prioritize | 2017
weq_oasis071916w2 (BPA Action Item Response)
3b | 2005-10-11 | 2008 | Enhance the TSR Results posting to allow a showing of limiting transmission elements for denied transmission service requests. This shall include information for denied Coordinated Requests. R05026 scoping statement completed by SRS and R12006. | R05026 | SRS Scoping statement | OS/BPS | Initial position paper received from BPS. No formal action take to date. | OS to prioritize | 2017
|  |  |  | R12006 | weq_oasis022416w2 (BPS response)
3a | 2005-10-11 | 2008 | Make remaining incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS (R05026). Scoping statement completed by SRS. There were a number of assignments from the Standards Request. The outstanding item is Enhance the TSR result postings to allow showing of available generation dispatch options that would allow acceptance of reservation request. | R05026 | SRS Scoping statement | OS/BPS | Initial position paper received from BPS. No formal action take to date. Follow BPS reccomendation to refer to SIS studies. BPS response addresses firm only. | OS to prioritize | 3rd Q 2017
weq_oasis022416w2 (BPS response)
3c | 2012-02-22 | 2013 | Requirements for OASIS to use data in the Electric Industry Registry | R12001 | None located | OS |  | OS to prioritize | TBD
1eiii | 2017-10-07 | 2017 | Assess Impact on NAESB Business Practice Standards and Specifications due to changes in tool ownership, NERC Committee Structure, and changes to the NERC Rules of Procedures. Review and modify as necessary WEQ-001, WEQ-002, WEQ-003, and WEQ-013 to address Line Items 2 through 17 from SRS Assignment Document | R16010 | SRS Scoping document | OS | SRS has assigned line items to OS | OS to prioritize | 3rd Q 2017
Make remaining incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS. Part One: Enhance the TSR result postings to allow showing of (i) limiting transmission elements
Improve transparency to allow customers to determine whether they have been treated in a non-discriminatory manner by posting of additional information on OASIS when service is denied (i.e. refused or declined) by customer(s) using new SAMTS process across multiple transmission systems to serve their NITS load on multiple systems. (R12006)
Enhance the TSR result postings to allow showing of (i) limiting transmission elements for denied transmission service requests. This shall include information for denied Coordinated Requests.

## API Ranking
NAESB WEQ-OASIS Subcommittee
2020 Annual Plan OPEN Items
2020 API to Review and Prioritize
2020 API # | Submitted Date | 1st Annual Plan Year | Description | Urgency Level 1-Very High Need 2-High Need 3- Moderate Need 4-Normal Need 5-Low Need | Effort Level 1-Very High Effort 2-High Effort 3-Moderate Effort 4-Normal Effort 5-Low Effort | Low Hanging Fruit Yes No | Time to Complete <6 months 6-12 months >12 months | Can Work be Done Outside Subcommittee Yes No | Priority Level | Priority Level 1-First 2-Second 3-Third 4-Fourth 5-Fifth | Request/FERC Order | Docs | Assigned | Status | Remaining Steps | Target Completion Date | Notes | Version Target
2a | 2007-10-11 | 2008 | Paragraph 1627 of Order 890 – Posting of additional information on OASIS regarding firm transmission curtailments | 3-Moderate Need | 2-High Effort | no |  |  | 5-Last | 1-First | 890 | weq_bps_oasis 090915w1 | OS/BPS | Issue item 1 and 2 has been assigned. | OS to prioritize | 2020 | Will work with BPS and their schedule and work plan | version 3.4
[11 empty] | 890A | weq_oasis062116a1 (BPA response)
890B
3a | 2012-02-22 | 2018 | Development of industry Business Practice Standards to define the eligibility and treatment of Rollover Rights for Network Integration Transmission Service (NITS). Also develop template structures and other standards that support these Business Practice Standards as necessary. (R18004) | 3-Moderate Need | 2-High Effort | no |  | yes | 5-Last | 1-First | R18004 |  | OS |  |  | 2020 | Formally 2019 API 3e | version 3.4
3b | 2012-02-22 | 2020 | Development of industry Business Practice Standards for the TP to be able to document any MW limitation on serving total load(s) as firm under the NITS Application at specific POD/Sink locations. This would be outside the scope of a load forecast (customer driven) | 3-Moderate Need | 3-Moderate Effort | no |  |  | 5-Last |  | N/A |  | OS |  |  | TBD | From Parking Lot for 2019 API 3c 06/26/19 looks to be complicated will keep on the list for future enhancements | version 3.4
3c | 2012-02-22 | 2020 | Development of industry Business Practice Standards for the need for expanding concept of generation groups. E.g., hierarchical groups - fleet, plant, unit | 3-Moderate Need | 3-Moderate Effort | no |  |  | 5-Last |  | Nevada Power |  | OS |  |  | TBD | From Parking Lot for 2019 API 3c 06/26/19 looks to be complicated will keep on the list for future enhancements | version 3.4
3d | 2012-02-22 | 2020 | Development of industry Business Practice Standards to look into the optional nature be removed to require creating of Scheduling Rights (SRs) whether requested by the customer or generated by the TP. | 3-Moderate Need | 3-Moderate Effort | no |  |  | 5-Last |  | N/A |  | OS |  |  | TBD | From Parking Lot for 2019 API 3c 07/16/19 Subcommittee will take this as an action item for the 07/23-25/19 meeting in Carmel 7/23/19 looks to be complicated will keep on the list for future enhancements | veriosn 3.4
3e | 2012-02-22 | 2020 | Development of industry Business Practice Standards for adding new variables on certain query responses (e.g., NITSLoadForecast, etc.) | 3-Moderate Need | 4-Normal Effort | yes |  | yes | 5-Last | 2-Second | N/A |  | OS |  |  | 2020 | From Parking Lot for 2019 API 3c 09/18/19 - subcommittee went through all the changes that Marilyn submitted and these items were flagged as items to be looked at in the future (APPLICATION_NAME, APPLICATION_NAME_LIST, RESOURCE_NAME_LIST, POR_LIST, POD_LIST, SINK_LIST | version 3.4

## API Rank-Priority (hidden)
NAESB WEQ-OASIS Subcommittee
2016 Annual Plan ItemPrioritization Worksheet
2016 API # | 1st Annual Plan Year | Description | Urgency Level | Effort Level | Easy to Complete? | Request/FERC Order | Docs | Assigned | Status | Remaining Steps | Target Completion Date
2aii1 | 2008 | Paragraph 1627 of Order 890 – Posting of additional information on OASIS regarding firm transmission curtailments |  |  |  | 890 | weq_bps_oasis 090915w1 | OS/BPS | Initial positionpaper received from BPS. BPA accepted an individual assignment to capture associated parameters and challenges. No formal action taken to date. | OS to prioritize
weq_oasis062116a1 (BPA response)
2aii2 | 2008 (2014?) | Redispatch Cost Posting to allow for posting of third party offers of planning redispatch services. |  |  |  | 890 | weq-0asis 022416a2 BPS Feb 2016 | OS/BPS | Initial positionpaper received from BPS. BPA accepted an individual assignment to capture associated parameters and challenges. No formal action taken to date. | OS to prioritize
weq_oasis071916w2 (BPA Action Item Response)
3a Part One | 2008 | Make remaining incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS. Part One: Enhance the TSR result postings to allow showing of (i) limiting transmission elements |  |  |  | R05026 | SRS Scoping statement | OS/BPS | Initial position paper received from BPS. No formal action take to date. | OS to prioritize
weq_oasis022416w2 (BPS response)
3a Part Two | 2008 | Make remaining incremental enhancements to OASIS as an outgrowth of the NAESB March 29, 2005 conference on the future of OASIS. Part Two: Enhance the TSR result postings to allow showing of (ii) available generation dispatch options that would allow acceptance of reservation request. |  |  |  | R05026 | SRS Scoping statement | OS/BPS | Initial position paper received from BPS. No formal action take to date. | OS to prioritize
weq_oasis022416w2 (BPS response)
3b | 2013 | Requirements for OASIS to use data in the Electric Industry Registry |  |  |  | R12001 | None located | OS |  | OS to prioritize
2ai1 | 2008 | Short-Term Firm Preemption and Competition (OATT Section 13.2 and 14.2) |  |  |  | R05019 | 2016 WEQ Annual Plan Items 2.a.i.1 and 5.a | OS | WEQ-001 out for informal comments. Comments due 11/11/2016 | WEQ-002,003,013 | 1st Q 2017
5a | 2010 | Add language to WEQ-001-4 Online Negotiation and Confirmation process to clarify Table 4-3 |  |  |  | R09003 |  | OS | WEQ-001 out for informal comments. Comments due 11/11/2016 | WEQ-002,003,013 | 1st Q 2017
5c | 2012 | Improve transparency to allow customers to determine whether they have been treated in a non-discriminatory manner by posting of additional information on OASIS when service is denied (i.e. refused or declined) by customer(s) using new SAMTS process across multiple transmission systems to serve their NITS load on multiple systems. (R12006) |  |  |  | R12006 | None received from BPS | OS/BPS | On hold at BPS | Await direction from BPS

## Rank table
Urgency level | Effort | Prior | yes/no | Easy |  | Time
1-Very High Need | 1-Very High Effort | 1-First | yes | <6 months | Urgency level 1- high industry need 5- low industry need | < 6 months
2-High Need | 2-High Effort | 2-Second | no | 6-12 months | Effort level 1- high work load 5 – low work load | 6-12 months
3-Moderate Need | 3-Moderate Effort | 3-Third |  | >12 months | Priority level 1- first on list to work on 2 – next, etc. | > 12 months
4- Normal Need | 4-Normal Effort | 4-Fourth
5-Low Need | 5- Low Effort | 5-Fifth
6-Last